## Export
Project No. | Hull Number | Vessel Name | IMO | Vessel Category | Charter | Charter Type | Builder Yard | Builder Country | Series | Alt. Fuel | Alt. Fuel Type | Contract Signing | Steel Cutting | Keel Laid | Launching | Sea Trial | Target Delivery | Actual Delivery | Contract Delivery | Charter Delivery | Fleet Key Event Status | Current Stage | Schedule Variance
1 | 0216001 | 0216001 | 1093559 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG | 2026-03-24 | 2026-05-05 | 2026-10-30 | 2027-01-24 |  | 2027-04-14 |  | 2027-06-30 |  |  | Not Started | -77
| 0216002 | 0216002 | 1093561 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG |  | 2026-06-12 | 2026-12-10 | 2027-04-04 |  | 2027-06-13 |  | 2027-08-15 |  |  | Not Started | -63
| 0216003 | 0216003 | 1093573 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG |  | 2026-07-31 | 2027-01-27 | 2027-05-24 |  | 2027-08-02 |  | 2027-09-30 |  |  | Not Started | -59
| 0216004 | 0216004 | 1093585 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG |  | 2026-09-30 | 2027-04-07 | 2027-07-18 |  | 2027-09-26 |  | 2027-11-30 |  |  | Not Started | -65
| 0216005 | 0216005 | 1093597 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG |  | 2027-01-12 | 2027-07-21 | 2027-10-13 |  | 2028-01-04 |  | 2028-01-23 |  |  | Not Started | -19
2 | 24110005 | Glovis Lander | 1063487 | PCTC | Glovis | Time Charter | CSSC GSI | China | 10800-GSI | Yes | LNG | 2024-03-11 | 2025-05-12 | 2025-10-28 | 2026-04-23 | 2026-06-22 | 2026-07-17 |  | 2026-12-31 |  | Outfitting | Launching | -167
| 24110006 | Glovis Luminous | 1063499 | PCTC | Glovis | Time Charter | CSSC GSI | China |  | Yes | LNG | 2024-03-11 | 2026-04-28 | 2026-11-09 | 2027-04-12 | 2027-06-12 | 2027-07-12 |  | 2027-11-30 |  |  | Steel Cutting | -141
3 | H1610 | Glovis Lighthouse | 1044340 | PCTC | Glovis | Time Charter | CSSC SWS | China |  | Yes | LNG |  | 2025-06-10 | 2025-12-17 | 2026-03-25 | 2026-05-11 | 2026-06-05 |  | 2026-11-30 |  | Outfitting | Launching | -178
| H1612 | Glovis Link | 1044364 | PCTC | Glovis | Time Charter | CSSC SWS | China |  | Yes | LNG |  | 2026-01-13 | 2026-07-26 | 2026-10-21 | 2026-11-29 | 2026-12-24 |  | 2027-06-30 |  | Block Stage | Steel Cutting | -188
| H1614 | Glovis Logos | 1044388 | PCTC | Glovis | Time Charter | CSSC SWS | China | 10800-SWS | Yes | LNG |  | 2026-04-23 | 2026-10-22 | 2027-01-09 | 2027-03-01 | 2027-03-26 |  | 2027-10-31 |  | Block Stage | Steel Cutting | -219
| H1615 | Glovis Loyal | 1044390 | PCTC | Glovis | Time Charter | CSSC SWS | China |  | Yes | LNG |  | 2026-06-02 | 2026-12-01 | 2027-03-03 | 2027-04-09 | 2027-05-06 |  | 2027-12-31 |  |  | Not Started | -239
4 | H1619 | COSCO SHIPPING GHANA | 1149114 | Containership | COSCO | Time Charter | CSSC SWS | China | 9200 SWS | No | Conventional |  | 2026-11-16 | 2027-05-31 | 2027-08-31 |  | 2027-11-30 |  | 2027-12-31 |  |  | Not Started | -31
| H1620 | COSCO SHIPPING SENEGAL | 1149126 | Containership | COSCO | Time Charter | CSSC SWS | China | 9200 SWS | No | Conventional |  | 2027-01-04 | 2027-07-31 | 2027-10-31 |  | 2028-01-31 |  | 2028-03-31 |  |  | Not Started | -60
| H1621 | COSCO SHIPPING BENIN | 1149138 | Containership | COSCO | Time Charter | CSSC SWS | China | 9200 SWS | No | Conventional |  | 2027-04-06 | 2027-10-31 | 2027-12-31 |  | 2028-03-31 |  | 2028-05-31 |  |  | Not Started | -61
| H1622 | COSCO SHIPPING NAMIBIA | 1149140 | Containership | COSCO | Time Charter | CSSC SWS | China | 9200 SWS | No | Conventional |  | 2027-05-31 | 2027-12-31 | 2028-03-31 |  | 2028-06-30 |  | 2028-07-31 |  |  | Not Started | -31
5 | H1668 | COSCO SHIPPING TOWNSVILLE |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-03-31 | 2027-10-31 | 2028-01-31 |  | 2028-05-31 |  | 2028-07-31 |  |  | Not Started | -61
| H1669 | COSCO SHIPPING TAURANGA |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-05-31 | 2027-11-30 | 2028-02-29 |  | 2028-06-30 |  | 2028-09-30 |  |  | Not Started | -92
| H1670 | COSCO SHIPPING PARANAGUA |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-06-30 | 2027-12-31 | 2028-04-30 |  | 2028-08-31 |  | 2028-10-31 |  |  | Not Started | -61
| H1671 | COSCO SHIPPING NAVEGANTES |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-08-31 | 2028-02-29 | 2028-06-30 |  | 2028-10-31 |  | 2028-11-30 |  |  | Not Started | -30
| H1672 | COSCO SHIPPING ITAJAI |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-09-30 | 2028-04-30 | 2028-07-31 |  | 2028-11-30 |  | 2028-12-31 |  |  | Not Started | -31
| H1673 | COSCO SHIPPING ITAPOA |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-11-30 | 2028-06-30 | 2028-09-30 |  | 2028-12-31 |  | 2028-12-31 |  |  | Not Started
6 | H1731 | ZIM Boston | 1140027 | Containership | ZIM | Time Charter | YZJ - Xinfu | China | 11800-YZJ | No | Conventional |  | 2026-04-23 | 2026-09-27 | 2027-03-27 |  | 2027-06-25 |  | 2027-08-30 |  | Block Stage | Steel Cutting | -66
| H1732 | ZIM Texas | 1140039 | Containership | ZIM | Time Charter | YZJ - Hongyuan | China | 11800-YZJ | No | Conventional |  | 2026-09-07 | 2027-02-04 | 2027-07-01 |  | 2027-09-29 |  | 2027-11-30 |  |  | Not Started | -62
7 | H1943A | OOCL Chancay | 1094151 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2025-08-19 | 2025-12-31 | 2026-06-01 | 2026-07-29 | 2026-08-28 |  | 2026-12-31 |  | Dock Stage | Keel Laying | -125
| H1944A | OOCL Peru | 1094163 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2025-09-29 | 2026-04-28 | 2026-08-27 | 2026-11-10 | 2026-12-10 |  | 2026-12-31 |  | Block Stage | Keel Laying | -21
| H1945A | OOCL Ecuador | 1094175 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2025-10-24 | 2026-04-17 | 2026-07-25 | 2026-09-24 | 2026-10-23 |  | 2027-02-28 |  | Dock Stage | Keel Laying | -128
| H1946A | OOCL Chile | 1094187 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2025-12-26 | 2026-06-03 | 2026-09-21 | 2026-12-17 | 2026-12-18 |  | 2027-03-31 |  | Block Stage | Steel Cutting | -103
| H1953A | OOCL Colombia | 1094199 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2026-12-28 | 2027-06-24 | 2027-10-14 | 2028-01-12 | 2028-01-04 |  | 2028-03-31 |  |  | Not Started | -87
| H1954A | OOCL Mexico | 1094204 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2027-02-25 | 2027-08-21 | 2027-12-07 | 2028-02-29 | 2028-03-06 |  | 2028-03-31 |  |  | Not Started | -25
8 | H1981A | COSCO SHIPPING NIGERIA | 1174860 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-01-06 | 2027-06-05 | 2027-09-03 |  | 2027-11-30 |  | 2027-11-30 |  |  | Not Started
| H1982A | COSCO SHIPPING ANGOLA | 1174872 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-02-01 | 2027-07-01 | 2027-10-22 |  | 2028-01-20 |  | 2027-12-31 |  |  | Not Started | 20
| H1983A | COSCO SHIPPING TOGO | 1174884 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-07-09 | 2027-12-06 | 2028-03-20 |  | 2028-06-18 |  | 2028-06-30 |  |  | Not Started | -12
| H1984A | COSCO SHIPPING CAMEROON | 1174896 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-05-26 | 2027-10-23 | 2028-03-03 |  | 2028-06-01 |  | 2028-08-31 |  |  | Not Started | -91
| H1985A | COSCO SHIPPING SOUTH AFRICA | 1174901 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-10-24 | 2028-03-22 | 2028-06-20 |  | 2028-09-18 |  | 2028-09-30 |  |  | Not Started | -12
| H1986A | COSCO SHIPPING KENYA | 1174913 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-10-10 | 2028-03-08 | 2028-06-29 |  | 2028-09-27 |  | 2028-10-31 |  |  | Not Started | -34
| H1987A | COSCO SHIPPING TANZANIA | 1174925 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-12-04 | 2028-05-02 | 2028-08-28 |  | 2028-11-26 |  | 2028-12-15 |  |  | Not Started | -19
| H1988A | COSCO SHIPPING MOZAMBIQUE | 1174937 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2028-01-24 | 2028-06-22 | 2028-09-16 |  | 2028-12-15 |  | 2028-12-31 |  |  | Not Started | -16
9 | H2907 | H2907 |  | Ethane Carrier | Future Ocean LNG | Bare Boat | CSSC Jiangnan | China | 100k-VLEC | Yes | Ethane |  | 2027-03-18 | 2027-09-21 | 2027-12-15 |  | 2028-05-15 |  | 2028-05-15 |  |  | Not Started
| H2908 | H2908 |  | Ethane Carrier | Future Ocean LNG | Bare Boat | CSSC Jiangnan | China | 100k-VLEC | Yes | Ethane |  | 2027-04-22 | 2027-11-04 | 2028-02-15 |  | 2028-06-30 |  | 2028-06-30 |  |  | Not Started
| H2909 | H2909 |  | Ethane Carrier | Future Ocean LNG | Bare Boat | CSSC Jiangnan | China | 100k-VLEC | Yes | Ethane |  | 2027-06-08 | 2027-12-20 | 2028-03-29 |  | 2028-08-15 |  | 2028-08-15 |  |  | Not Started
10 | NDY6001 | NDY6001 |  | Bulk Carrier | Gearbulk | Bare Boat | New Dayang Shipbuilding | China | 65,200 DWT OHGC | No | Conventional | 2026-04-14 | 2028-03-06 | 2028-10-09 | 2028-12-22 |  | 2029-06-29 |  | 2029-06-29 |  |  | Not Started
| NDY6002 | NDY6002 |  | Bulk Carrier | Gearbulk | Bare Boat | New Dayang Shipbuilding | China | 65,200 DWT OHGC | No | Conventional | 2026-04-14 | 2028-03-03 | 2028-10-09 | 2028-12-22 |  | 2029-06-30 |  | 2029-06-30 |  |  | Not Started
| NDY6003 | NDY6003 |  | Bulk Carrier | Gearbulk | Bare Boat | New Dayang Shipbuilding | China | 65,200 DWT OHGC | No | Conventional | 2026-04-14 | 2028-05-29 | 2029-01-20 | 2029-04-29 |  | 2029-08-20 |  | 2029-08-20 |  |  | Not Started
| NDY6004 | NDY6004 |  | Bulk Carrier | Gearbulk | Bare Boat | New Dayang Shipbuilding | China | 65,200 DWT OHGC | No | Conventional | 2026-04-14 | 2028-06-12 | 2029-01-20 | 2029-04-29 |  | 2029-08-30 |  | 2029-08-30 |  |  | Not Started
11 | YZJ2024-1660 | YZJ2024-1660 | 1107192 | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | Methanol |  | 2026-09-29 | 2027-02-26 | 2027-06-21 |  | 2027-10-09 |  | 2027-10-30 |  |  | Not Started | -21
| YZJ2024-1661 | YZJ2024-1661 | 1107207 | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | Methanol |  | 2026-11-23 | 2027-04-22 | 2027-08-20 |  | 2027-12-08 |  | 2027-12-30 |  |  | Not Started | -22
| YZJ2024-1662 | YZJ2024-1662 | 1107219 | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | Methanol |  | 2027-01-25 | 2027-06-24 | 2027-10-22 |  | 2028-02-24 |  | 2028-03-15 |  |  | Not Started | -20
| YZJ2024-1663 | YZJ2024-1663 | 1107221 | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | Methanol |  | 2027-03-26 | 2027-08-23 | 2027-12-19 |  | 2028-04-22 |  | 2028-05-15 |  |  | Not Started | -23
| YZJ2024-1664 | YZJ2024-1664 |  | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | LNG |  | 2027-05-28 | 2027-10-25 | 2028-03-03 |  | 2028-06-21 |  | 2028-07-15 |  |  | Not Started | -24
| YZJ2024-1665 | YZJ2024-1665 |  | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | LNG |  | 2027-07-25 | 2027-12-22 | 2028-04-30 |  | 2028-08-18 |  | 2028-09-15 |  |  | Not Started | -28
| YZJ2024-1666 | YZJ2024-1666 |  | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | LNG |  | 2027-10-08 | 2028-03-06 | 2028-06-29 |  | 2028-10-17 |  | 2028-11-15 |  |  | Not Started | -29
| YZJ2024-1667 | YZJ2024-1667 |  | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | LNG |  | 2027-12-05 | 2028-05-03 | 2028-09-05 |  | 2028-12-24 |  | 2028-12-31 |  |  | Not Started | -7
12 | YZJ2024-1674 | YZJ2024-1674 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2027-06-04 | 2027-11-01 | 2028-03-21 |  | 2028-06-24 |  | 2028-07-30 |  |  | Not Started | -36
| YZJ2024-1677 | YZJ2024-1677 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2027-12-16 | 2028-05-29 | 2028-10-07 |  | 2029-01-10 |  | 2028-12-31 |  |  | Not Started | 10
| YZJ2024-1678 | YZJ2024-1678 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2027-12-16 | 2028-05-29 | 2028-10-07 |  | 2029-01-25 |  | 2029-03-25 |  |  | Not Started | -59
| YZJ2024-1680 | YZJ2024-1680 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2028-03-10 | 2028-08-07 | 2028-12-11 |  | 2029-03-31 |  | 2029-06-05 |  |  | Not Started | -66
| YZJ2024-1681 | YZJ2024-1681 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2028-03-10 | 2028-08-07 | 2028-12-11 |  | 2029-04-15 |  | 2029-06-20 |  |  | Not Started | -66
| YZJ2024-1682 | YZJ2024-1682 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2028-05-14 | 2028-10-11 | 2029-03-01 |  | 2029-06-04 |  | 2029-08-20 |  |  | Not Started | -77
13 | YZJ2024-1673 | YZJ2024-1673 |  | Containership | Maersk | Time Charter | YZJ - Hongyuan | China | 17000-YZJ | Yes | LNG |  | 2027-01-21 | 2027-07-05 | 2027-10-29 |  | 2028-03-02 |  | 2028-04-30 |  |  | Not Started | -59
| YZJ2024-1675 | YZJ2024-1675 |  | Containership | Maersk | Time Charter | YZJ - Hongyuan | China | 17000-YZJ | Yes | LNG |  | 2027-10-03 | 2028-03-16 | 2028-07-08 |  | 2028-10-26 |  | 2028-10-30 |  |  | Not Started | -4
| YZJ2024-1676 | YZJ2024-1676 |  | Containership | Maersk | Time Charter | YZJ - Hongyuan | China | 17000-YZJ | Yes | LNG |  | 2027-11-30 | 2028-05-13 | 2028-09-09 |  | 2028-12-15 |  | 2028-12-15 |  |  | Not Started
| YZJ2024-1679 | YZJ2024-1679 |  | Containership | Maersk | Time Charter | YZJ - Hongyuan | China | 17000-YZJ | Yes | LNG |  | 2028-04-16 | 2028-09-13 | 2029-01-07 |  | 2029-04-30 |  | 2029-04-10 |  |  | Not Started | 20
| YZJ2024-1685 | YZJ2024-1685 |  | Containership | ONE | Time Charter | YZJ - Hongyuan | China | 13000-YZJ | Yes | LNG |  | 2028-01-27 | 2028-07-10 | 2028-11-06 |  | 2029-01-31 |  | 2028-12-30 |  |  | Not Started | 32

## og (hidden)
Hull Number | Vessel Name | IMO | Vessel Category | Charter | Charter Type | Builder Yard | Builder Country | Series | Alt. Fuel | Alt. Fuel Type | Contract Signing | Steel Cutting | Keel Laid | Launching | Sea Trial | Target Delivery | Actual Delivery | Contract Delivery | Charter Delivery | Fleet Key Event Status | Current Stage | Schedule Variance
0216001 | 0216001 | 1093559 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG | 2026-03-24 | 2026-05-05 | 2026-10-30 | 2027-01-24 |  | 2027-04-14 |  | 2027-06-30 |  |  | Not Started | -77
0216002 | 0216002 | 1093561 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG |  | 2026-06-12 | 2026-12-10 | 2027-04-04 |  | 2027-06-13 |  | 2027-08-15 |  |  | Not Started | -63
0216003 | 0216003 | 1093573 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG |  | 2026-07-31 | 2027-01-27 | 2027-05-24 |  | 2027-08-02 |  | 2027-09-30 |  |  | Not Started | -59
0216004 | 0216004 | 1093585 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG |  | 2026-09-30 | 2027-04-07 | 2027-07-18 |  | 2027-09-26 |  | 2027-11-30 |  |  | Not Started | -65
0216005 | 0216005 | 1093597 | Containership | Maersk | Time Charter | NTS | China | 16000-NTS | Yes | LNG |  | 2027-01-12 | 2027-07-21 | 2027-10-13 |  | 2028-01-04 |  | 2028-01-23 |  |  | Not Started | -19
24110005 | Glovis Lander | 1063487 | PCTC | Glovis | Time Charter | CSSC GSI | China | 10800-GSI | Yes | LNG | 2024-03-11 | 2025-05-12 | 2025-10-28 | 2026-04-23 | 2026-06-22 | 2026-07-17 |  | 2026-12-31 |  | Outfitting | Launching | -167
24110006 | Glovis Luminous | 1063499 | PCTC | Glovis | Time Charter | CSSC GSI | China |  | Yes | LNG | 2024-03-11 | 2026-04-28 | 2026-11-09 | 2027-04-12 | 2027-06-12 | 2027-07-12 |  | 2027-11-30 |  |  | Steel Cutting | -141
H1610 | Glovis Lighthouse | 1044340 | PCTC | Glovis | Time Charter | CSSC SWS | China |  | Yes | LNG |  | 2025-06-10 | 2025-12-17 | 2026-03-25 | 2026-05-11 | 2026-06-05 |  | 2026-11-30 |  | Outfitting | Launching | -178
H1612 | Glovis Link | 1044364 | PCTC | Glovis | Time Charter | CSSC SWS | China |  | Yes | LNG |  | 2026-01-13 | 2026-07-26 | 2026-10-21 | 2026-11-29 | 2026-12-24 |  | 2027-06-30 |  | Block Stage | Steel Cutting | -188
H1614 | Glovis Logos | 1044388 | PCTC | Glovis | Time Charter | CSSC SWS | China | 10800-SWS | Yes | LNG |  | 2026-04-23 | 2026-10-22 | 2027-01-09 | 2027-03-01 | 2027-03-26 |  | 2027-10-31 |  | Block Stage | Steel Cutting | -219
H1615 | Glovis Loyal | 1044390 | PCTC | Glovis | Time Charter | CSSC SWS | China |  | Yes | LNG |  | 2026-06-02 | 2026-12-01 | 2027-03-03 | 2027-04-09 | 2027-05-06 |  | 2027-12-31 |  |  | Not Started | -239
H1619 | COSCO SHIPPING GHANA | 1149114 | Containership | COSCO | Time Charter | CSSC SWS | China | 9200 SWS | No | Conventional |  | 2026-11-16 | 2027-05-31 | 2027-08-31 |  | 2027-11-30 |  | 2027-12-31 |  |  | Not Started | -31
H1620 | COSCO SHIPPING SENEGAL | 1149126 | Containership | COSCO | Time Charter | CSSC SWS | China | 9200 SWS | No | Conventional |  | 2027-01-04 | 2027-07-31 | 2027-10-31 |  | 2028-01-31 |  | 2028-03-31 |  |  | Not Started | -60
H1621 | COSCO SHIPPING BENIN | 1149138 | Containership | COSCO | Time Charter | CSSC SWS | China | 9200 SWS | No | Conventional |  | 2027-04-06 | 2027-10-31 | 2027-12-31 |  | 2028-03-31 |  | 2028-05-31 |  |  | Not Started | -61
H1622 | COSCO SHIPPING NAMIBIA | 1149140 | Containership | COSCO | Time Charter | CSSC SWS | China | 9200 SWS | No | Conventional |  | 2027-05-31 | 2027-12-31 | 2028-03-31 |  | 2028-06-30 |  | 2028-07-31 |  |  | Not Started | -31
H1668 | COSCO SHIPPING TOWNSVILLE |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-03-31 | 2027-10-31 | 2028-01-31 |  | 2028-05-31 |  | 2028-07-31 |  |  | Not Started | -61
H1669 | COSCO SHIPPING TAURANGA |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-05-31 | 2027-11-30 | 2028-02-29 |  | 2028-06-30 |  | 2028-09-30 |  |  | Not Started | -92
H1670 | COSCO SHIPPING PARANAGUA |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-06-30 | 2027-12-31 | 2028-04-30 |  | 2028-08-31 |  | 2028-10-31 |  |  | Not Started | -61
H1671 | COSCO SHIPPING NAVEGANTES |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-08-31 | 2028-02-29 | 2028-06-30 |  | 2028-10-31 |  | 2028-11-30 |  |  | Not Started | -30
H1672 | COSCO SHIPPING ITAJAI |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-09-30 | 2028-04-30 | 2028-07-31 |  | 2028-11-30 |  | 2028-12-31 |  |  | Not Started | -31
H1673 | COSCO SHIPPING ITAPOA |  | Containership | COSCO | Time Charter | CSSC SWS | China | 11400 | No | Conventional |  | 2027-11-30 | 2028-06-30 | 2028-09-30 |  | 2028-12-31 |  | 2028-12-31 |  |  | Not Started
H1731 | ZIM Boston | 1140027 | Containership | ZIM | Time Charter | YZJ - Xinfu | China | 11800-YZJ | No | Conventional |  | 2026-04-23 | 2026-09-27 | 2027-03-27 |  | 2027-06-25 |  | 2027-08-30 |  | Block Stage | Steel Cutting | -66
H1732 | ZIM Texas | 1140039 | Containership | ZIM | Time Charter | YZJ - Hongyuan | China | 11800-YZJ | No | Conventional |  | 2026-09-07 | 2027-02-04 | 2027-07-01 |  | 2027-09-29 |  | 2027-11-30 |  |  | Not Started | -62
H1943A | OOCL Chancay | 1094151 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2025-08-19 | 2025-12-31 | 2026-06-01 | 2026-07-29 | 2026-08-28 |  | 2026-12-31 |  | Dock Stage | Keel Laying | -125
H1944A | OOCL Peru | 1094163 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2025-09-29 | 2026-04-28 | 2026-08-27 | 2026-11-10 | 2026-12-10 |  | 2026-12-31 |  | Block Stage | Keel Laying | -21
H1945A | OOCL Ecuador | 1094175 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2025-10-24 | 2026-04-17 | 2026-07-25 | 2026-09-24 | 2026-10-23 |  | 2027-02-28 |  | Dock Stage | Keel Laying | -128
H1946A | OOCL Chile | 1094187 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2025-12-26 | 2026-06-03 | 2026-09-21 | 2026-12-17 | 2026-12-18 |  | 2027-03-31 |  | Block Stage | Steel Cutting | -103
H1953A | OOCL Colombia | 1094199 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2026-12-28 | 2027-06-24 | 2027-10-14 | 2028-01-12 | 2028-01-04 |  | 2028-03-31 |  |  | Not Started | -87
H1954A | OOCL Mexico | 1094204 | Containership | OOCL | Time Charter | CSSC Hudong | China | 13600-HZ | No | Conventional |  | 2027-02-25 | 2027-08-21 | 2027-12-07 | 2028-02-29 | 2028-03-06 |  | 2028-03-31 |  |  | Not Started | -25
H1981A | COSCO SHIPPING NIGERIA | 1174860 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-01-06 | 2027-06-05 | 2027-09-03 |  | 2027-11-30 |  | 2027-11-30 |  |  | Not Started
H1982A | COSCO SHIPPING ANGOLA | 1174872 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-02-01 | 2027-07-01 | 2027-10-22 |  | 2028-01-20 |  | 2027-12-31 |  |  | Not Started | 20
H1983A | COSCO SHIPPING TOGO | 1174884 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-07-09 | 2027-12-06 | 2028-03-20 |  | 2028-06-18 |  | 2028-06-30 |  |  | Not Started | -12
H1984A | COSCO SHIPPING CAMEROON | 1174896 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-05-26 | 2027-10-23 | 2028-03-03 |  | 2028-06-01 |  | 2028-08-31 |  |  | Not Started | -91
H1985A | COSCO SHIPPING SOUTH AFRICA | 1174901 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-10-24 | 2028-03-22 | 2028-06-20 |  | 2028-09-18 |  | 2028-09-30 |  |  | Not Started | -12
H1986A | COSCO SHIPPING KENYA | 1174913 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-10-10 | 2028-03-08 | 2028-06-29 |  | 2028-09-27 |  | 2028-10-31 |  |  | Not Started | -34
H1987A | COSCO SHIPPING TANZANIA | 1174925 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2027-12-04 | 2028-05-02 | 2028-08-28 |  | 2028-11-26 |  | 2028-12-15 |  |  | Not Started | -19
H1988A | COSCO SHIPPING MOZAMBIQUE | 1174937 | Containership | COSCO | Time Charter | CSSC Hudong | China | 9040 HZ | No | Conventional |  | 2028-01-24 | 2028-06-22 | 2028-09-16 |  | 2028-12-15 |  | 2028-12-31 |  |  | Not Started | -16
H2907 | H2907 |  | Ethane Carrier | Future Ocean LNG | Bare Boat | CSSC Jiangnan | China | 100k-VLEC | Yes | Ethane |  | 2027-03-18 | 2027-09-21 | 2027-12-15 |  | 2028-05-15 |  | 2028-05-15 |  |  | Not Started
H2908 | H2908 |  | Ethane Carrier | Future Ocean LNG | Bare Boat | CSSC Jiangnan | China | 100k-VLEC | Yes | Ethane |  | 2027-04-22 | 2027-11-04 | 2028-02-15 |  | 2028-06-30 |  | 2028-06-30 |  |  | Not Started
H2909 | H2909 |  | Ethane Carrier | Future Ocean LNG | Bare Boat | CSSC Jiangnan | China | 100k-VLEC | Yes | Ethane |  | 2027-06-08 | 2027-12-20 | 2028-03-29 |  | 2028-08-15 |  | 2028-08-15 |  |  | Not Started
NDY6001 | NDY6001 |  | Bulk Carrier | Gearbulk | Bare Boat | New Dayang Shipbuilding | China | 65,200 DWT OHGC | No | Conventional | 2026-04-14 | 2028-03-06 | 2028-10-09 | 2028-12-22 |  | 2029-06-29 |  | 2029-06-29 |  |  | Not Started
NDY6002 | NDY6002 |  | Bulk Carrier | Gearbulk | Bare Boat | New Dayang Shipbuilding | China | 65,200 DWT OHGC | No | Conventional | 2026-04-14 | 2028-03-03 | 2028-10-09 | 2028-12-22 |  | 2029-06-30 |  | 2029-06-30 |  |  | Not Started
NDY6003 | NDY6003 |  | Bulk Carrier | Gearbulk | Bare Boat | New Dayang Shipbuilding | China | 65,200 DWT OHGC | No | Conventional | 2026-04-14 | 2028-05-29 | 2029-01-20 | 2029-04-29 |  | 2029-08-20 |  | 2029-08-20 |  |  | Not Started
NDY6004 | NDY6004 |  | Bulk Carrier | Gearbulk | Bare Boat | New Dayang Shipbuilding | China | 65,200 DWT OHGC | No | Conventional | 2026-04-14 | 2028-06-12 | 2029-01-20 | 2029-04-29 |  | 2029-08-30 |  | 2029-08-30 |  |  | Not Started
YZJ2024-1660 | YZJ2024-1660 | 1107192 | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | Methanol |  | 2026-09-29 | 2027-02-26 | 2027-06-21 |  | 2027-10-09 |  | 2027-10-30 |  |  | Not Started | -21
YZJ2024-1661 | YZJ2024-1661 | 1107207 | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | Methanol |  | 2026-11-23 | 2027-04-22 | 2027-08-20 |  | 2027-12-08 |  | 2027-12-30 |  |  | Not Started | -22
YZJ2024-1662 | YZJ2024-1662 | 1107219 | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | Methanol |  | 2027-01-25 | 2027-06-24 | 2027-10-22 |  | 2028-02-24 |  | 2028-03-15 |  |  | Not Started | -20
YZJ2024-1663 | YZJ2024-1663 | 1107221 | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | Methanol |  | 2027-03-26 | 2027-08-23 | 2027-12-19 |  | 2028-04-22 |  | 2028-05-15 |  |  | Not Started | -23
YZJ2024-1664 | YZJ2024-1664 |  | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | LNG |  | 2027-05-28 | 2027-10-25 | 2028-03-03 |  | 2028-06-21 |  | 2028-07-15 |  |  | Not Started | -24
YZJ2024-1665 | YZJ2024-1665 |  | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | LNG |  | 2027-07-25 | 2027-12-22 | 2028-04-30 |  | 2028-08-18 |  | 2028-09-15 |  |  | Not Started | -28
YZJ2024-1666 | YZJ2024-1666 |  | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | LNG |  | 2027-10-08 | 2028-03-06 | 2028-06-29 |  | 2028-10-17 |  | 2028-11-15 |  |  | Not Started | -29
YZJ2024-1667 | YZJ2024-1667 |  | Containership | Maersk | Time Charter | YZJ - New | China | 9000-YZJ | Yes | LNG |  | 2027-12-05 | 2028-05-03 | 2028-09-05 |  | 2028-12-24 |  | 2028-12-31 |  |  | Not Started | -7
YZJ2024-1674 | YZJ2024-1674 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2027-06-04 | 2027-11-01 | 2028-03-21 |  | 2028-06-24 |  | 2028-07-30 |  |  | Not Started | -36
YZJ2024-1675 | YZJ2024-1675 |  | Containership | Maersk | Time Charter | YZJ - Hongyuan | China | 17000-YZJ | Yes | LNG |  | 2027-10-03 | 2028-03-16 | 2028-07-08 |  | 2028-10-26 |  | 2028-10-30 |  |  | Not Started | -4
YZJ2024-1676 | YZJ2024-1676 |  | Containership | Maersk | Time Charter | YZJ - Hongyuan | China | 17000-YZJ | Yes | LNG |  | 2027-11-30 | 2028-05-13 | 2028-09-09 |  | 2028-12-15 |  | 2028-12-15 |  |  | Not Started
YZJ2024-1677 | YZJ2024-1677 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2027-12-16 | 2028-05-29 | 2028-10-07 |  | 2029-01-10 |  | 2028-12-31 |  |  | Not Started | 10
YZJ2024-1678 | YZJ2024-1678 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2027-12-16 | 2028-05-29 | 2028-10-07 |  | 2029-01-25 |  | 2029-03-25 |  |  | Not Started | -59
YZJ2024-1679 | YZJ2024-1679 |  | Containership | Maersk | Time Charter | YZJ - Hongyuan | China | 17000-YZJ | Yes | LNG |  | 2028-04-16 | 2028-09-13 | 2029-01-07 |  | 2029-04-30 |  | 2029-04-10 |  |  | Not Started | 20
YZJ2024-1680 | YZJ2024-1680 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2028-03-10 | 2028-08-07 | 2028-12-11 |  | 2029-03-31 |  | 2029-06-05 |  |  | Not Started | -66
YZJ2024-1681 | YZJ2024-1681 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2028-03-10 | 2028-08-07 | 2028-12-11 |  | 2029-04-15 |  | 2029-06-20 |  |  | Not Started | -66
YZJ2024-1682 | YZJ2024-1682 |  | Containership | Maersk | Time Charter | YZJ - Xinfu | China | 17000-YZJ | Yes | LNG |  | 2028-05-14 | 2028-10-11 | 2029-03-01 |  | 2029-06-04 |  | 2029-08-20 |  |  | Not Started | -77
YZJ2024-1685 | YZJ2024-1685 |  | Containership | ONE | Time Charter | YZJ - Hongyuan | China | 13000-YZJ | Yes | LNG |  | 2028-01-27 | 2028-07-10 | 2028-11-06 |  | 2029-01-31 |  | 2028-12-30 |  |  | Not Started | 32